## Slide 1
1
SAP ID | JIRA ID | PM/BP | Business Owner | Involved DIvisions
I/00086 | PMO-176 | Papoutsi Stella | DDDE | DDDE, IT, Finance & Control, Commercial
Overall | Schedule | Cost | Scope
Project Status | Work Completed (%) | Baseline Budget | Planned Start Date | Planned/Estimated Completion Date
Analysis | 15 | 245K | 11 April 25 | 31 May 26
Phases/Milestones/Deliverables | R/A/G | Estimated Delivery Date | Remarks on progress
Setup the new Fabric platform | G | 30/4/2025 | Completed
Implementation of the data model | G | 14/5/2026 | In progress
User reports | G | 31/5/2026 | Pending
Project Name | Data Fabric and Advanced Analytics
Activities Performed & Milestones Achieved | Major Action Items - Upcoming Activities – Comments
Kick-Off: The project kick-off took place on April 11th, successfully aligning all teams on scope, roles, and timelines. Workshops Completed: Technical integration with IEBS, EFS, and Salesforce Billing data ingestion Main Business Workshop ¦ EES Business Workshop ¦ Sales & Marketing (SME & Large Accounts) All remaining workshops are scheduled to be completed by July 16th. | Technical integration with SAP. Salesforce and Collection data ingestion. IT Workshop focused on Salesforce and Billing. Business Workshop covering Billing and Customer Care. Data Model workshops. Additional Actions: Monitor and manage any rescheduling of workshops to prevent further delays. Prepare and distribute all necessary workshop materials to ensure productive sessions. Begin consolidating and analyzing the inputs gathered from workshops starting after July 16th.
Risk | Risk Assessment | Control
Resource Availability | M | Assign backup participants who can represent their functions.
Potential delays due to external vendors availability | M | Ensure engagement with external vendors for consultation sessions.
Stakeholder Misalignment | M | Conduct regular stakeholder alignment meetings to clarify goals and manage expectations.
Project Scope | To enhance Elpedison's data integration, governance, and analytics capabilities by adopting Microsoft Fabric Data and Advanced Analytics Platform. This initiative aims to create a unified architecture that addresses the organization's growing data needs and supports digital transformation.

## Slide 2
2
SAP ID | JIRA ID | PM/BP | Business Owner | Involved Divisions
H/00050 | PMO-198 | Papoutsi Stella | Commercial | DDDE, IT, Commercial
Overall | Schedule | Cost | Scope
Project Status | Work Completed (%) | Baseline Budget | Planned Start Date | Planned/Estimated Completion Date
Planning | 40 | 50K | 1 July 2025 | 28 Nov 2025
Project Name | Connection with egov-KYC
Activities Performed & Milestones Achieved | Major Action Items - Upcoming Activities - Comments
Project investment was officially approved on March 17th Phase A (MVP implementation in Salesforce) has been successfully completed. The Project Scope Document (PSD) was delivered on June 13th, following the completion of business requirements. Project Plan was delivered on June 30th after alignment with IT, Business & Vendor. | It was agreed that the Change Ticket (CT) to Singular would be split into two parts: The first CT, involving the addition of a New Meter/Supply Request, will be implemented and go live by July 29th, 2025. The remaining CTs, are scheduled for implementation and go-live by November 28th, 2025. Pending procurement actions in finalizing Vendor financial offer
Risk | Risk Assessment | Control
Increase demand for IT & DD&DE resources due to concurrent projects. | Μ | Perform detailed project planning and align with other projects. Carry out preparatory activities in parallel to avoid resource strain.
Limited engagement from vendor due to resource allocation | M | Conduct follow-up meetings with the vendor to ensure future availability and adjust the timeline based on the agreed plan.
Technical Challenges in API Integration | Μ | Issues in data retrieval from external sources (Greek IRS, GSIS, Hellenic Police) may delay system implementation. Perform early-stage testing and involve technical teams from both sides for seamless integration troubleshooting.
Project Scope | Develop a digital infrastructure that enables sales agents and back-office users to securely obtain customer identification data through a government web service. The expected Outcome is a fully digital, paperless, and efficient method for verifying customer identity, streamlining the application process for all stakeholders
2/21
Phases/Milestones/Deliverables | R/A/G | Estimated Delivery Date | Remarks on progress
PSD Finalization | G | 13/6/2025 | Completed
Phase B Kick-off | G | TBD | TBD
System Integration Kick-off | G | TBD | 
Development of backend services | G | TBD | 
Testing & Quality Assurance (UAT) | G | TBD | 
Go-Live | G | TBD | 

## Slide 3
3
SAP ID | JIRA ID | PM/BP | Business Owner | Involved Divisions
R/00036 | PMO-199 | Papoutsi Stella | Legal | DDDE, IT, Legal, Commercial, EES
Overall | Schedule | Cost | Scope
Project Status | Work Completed (%) | Baseline Budget | Planned Start Date | Planned/Estimated Completion Date
Planning | 5 | 23K | TBD | TBD
Phases/Milestones/Deliverables | R/A/G | Estimated Delivery Date | Remarks on progress
Project Kick-Off & Scope Alignment | G | TBD (After vendor evaluation) | Pending
Requirements Gathering & Process Mapping | G | TBD (After vendor evaluation) | Pending
Phase A: Customer Care Requests Management | G | TBD (After vendor evaluation) | Pending
Phase B: EES Department Contracts | G | TBD (After vendor evaluation) | Pending
Testing & Quality Assurance (UAT) | G | TBD (After vendor evaluation) | Pending
Final Review & Go-Live | G | TBD (After vendor evaluation) | Pending
Project Name | Legal Portal
Activities Performed & Milestones Achieved | Major Action Items - Upcoming Activities - Comments
Project received investment approval on March 17th. Conducted a meeting with the vendor to provide them with specifications related to the PSD. Agreement reached to proceed with the current workflow for internal clients only. Business Requirements Document submitted on May 7th. | Internal Project Kickoff - Hold a project kickoff meeting with internal stakeholders. Finalize and approve the project plan by mid-July. Pending procurement actions in finalizing financial offer from Vendor.
Risk | Risk Assessment | Control
Vendor Performance Issues | M | Ensure the vendor provides regular progress updates and maintains a buffer time in the timeline for unexpected delays
Vendor Onboarding Delays | L | Initiate the selection process early and engage key stakeholders from the beginning.
Project Scope | Automate the Legal Department’s work processing to minimize human error. Improve response times based on the urgency of each matter. Enhance record management and overall efficiency of the legal team through a digital tool.
3/21

## Slide 4
4
SAP ID | JIRA ID | PM/BP | Business Owner | Involved Divisions
L/00089 | ID-114 | Spanou/Tsetsos | Commercial | Commercial, DDDE,IT
Overall | Schedule | Cost | Scope
Project Status | Work Completed (%) | Baseline Budget | Planned Start Date | Planned/Estimated Completion Date
Implementation | 90% | 80K | 15 May 2024 | 29 Jule 2025
Project Name | My Elpedison Roadmap 2024
Project Scope | The scope of myElpedison is to develop and launch enhancements to the web and mobile platforms, providing a self-service and user-friendly experience with a wide range of features. These improvements aim to reduce OPEX and align with market trends and customer needs.
Key Deliverables | R/A/G | Delivery Date | Remarks on progress
Documenting requirements and preparatory sessions | G | 30/6/2024 | Completed
Vendor negotiation, estimation of effort, and discussion to resolve queries | G | 17/9/2024 | Completed
Deciding on implementation based on vendor feedback and effort estimates | G | 20/9/2024 | Completed
The implementation phase will be worked in 4 batches, following the process: Analysis of Business need→ Technical Analysis →Data Management review → Specifications Finalization → Vendor Effort Estimation → Implementation → Testing → GO-live. Note: The timeline for each batch is dynamic and will depend on the effort estimation provided by the vendor for each CR. Specific dates for each phase will be finalized as we progress. | A | 29/7/2025 | In Progress
Activities Performed & Milestones Achieved | Major Action Items - Upcoming Activities - Comments
The first three batches, including a total of 16 CRs, are now live across all platforms (Web, iOS, Android, Huawei). The third batch (Campaigns, Performance, Apple Pay Integration, DeepLink, Zero Balance Mandate, MFA) went live on 27/05/2025. The 4th batch is currently under implementation and will conclude the My Elpedison 2024 roadmap. | The 4th batch includes the following CRs: Relocation Request, Outstanding Balance Arrangement, Wording Improvements, Validation for Existing Arrangement, Payment Issue on iOS, Campaigns Dashboard, New Supply Request, GOV Data Update Go-live: 29/07/2025 This release marks the completion of the My Elpedison 2024 roadmap.
Risk | Risk Assessment | Mitigation Actions
Resource Allocation | M | Schedule specific calls and trainings to ensure resources are available and skilled to meet project deadlines.
Delays in vendor negotiations and effort estimation | Μ | Regular follow-ups with the vendor/ procurement and clear communication of requirements to expedite the process.
Quality of UAT Deliverables | M | To mitigate the risk of unsatisfactory UAT results affecting the feature launch time, we will implement thorough UAT plans and regular reviews to ensure quality standards are met before proceeding.

## Slide 5
5
SAP ID | JIRA ID | PM/BP | Business Owner | Involved Divisions
Ι/00067 | ID-229 | Spanou/Tsetsos | DD&DE | DDDE,IT
Overall | Schedule | Cost | Scope
Project Status | Work Completed (%) | Baseline Budget | Planned Start Date | Planned/Estimated Completion Date
Implementation | 95% | 75K | 20 May 2024 | 14 July 2025
Project Name | Digital Project Management, Collaboration & Monitoring Tool (Jira)
Project Scope | The Digital Development Department proposes the acquisition of a new tool to facilitate the effective and efficient management of all new Digital Development projects and initiatives
Key Deliverables | R/A/G | Delivery Date | Remarks on progress
Preparatory Meetings to Define High-Level Needs | G | Summer 2024 | Completed. Initial discussions held to identify high-level requirements.
Vendor Negotiation & Contract Signing | G | 4/9/24 | Completed
Functional Specifications & Analysis Workshops | G | 14/2/25 | Final version of FS document signed off.
Implementation | G | 19/3/25 | Completed
UAT Trainings | G | 28/3/25 | Completed
User Acceptance Testing (UAT) | G | 21/5/25 | UAT phase completed. All stakeholders confirmed sign-off. No critical blockers identified.
Go-Live | G | 29/5/25 | Completed
Key User Trainings | G | 13/6/25 | Completed
Admin Trainings | G | 18/6/25 | Completed
Jira Licenses | G | In progress | Internal discussions are ongoing to assess whether additional Jira licenses need to be purchased, based on actual user demand across teams. A decision on the required number is expected within the week, to proceed with the final purchase.
Risk | Risk Assessment | Mitigation Actions
Unclear or delayed definition of the licensing scheme may impact user access and cost control. | Μ | Finalize licensing model with vendor and IT. Include clear ownership and cost tracking responsibilities.
Low user adoption of the new Jira system may reduce the effectiveness of the solution. | Μ | Targeted training sessions have been planned to address this risk and ensure smooth onboarding.
Activities Performed & Milestones Achieved | Major Action Items - Upcoming Activities - Comments
Roll-out Phase: Successfully completed on 29/5/2025, including all migration actions from Nimaworks and Elpedison. Project Renaming: Digital Portal renaming completed on 2/6/2025. Admin & User Trainings: Successfully completed (13/6/2025 for Users, 17–18/6/2025 for Admins). | Licensing: Final decision pending on the number of additional licenses to be procured. Discussions ongoing with IT and Procurement. Payments: Pending processing by Accounting.

## Slide 6
6
SAP ID | JIRA ID | PM/BP | Business Owner | Involved Divisions
R/00034 | ID-367 | Spanou | IT | DDDE,IT
Overall | Schedule | Cost | Scope
Project Status | Work Completed (%) | Baseline Budget | Planned Start Date | Planned/Estimated Completion Date
Implemenation | 10% | 400K | 12 May 2025 | 15 Jan 2027
Project Name | Digitization Forms & Flows (UpPair Platform)
Project Scope | The project aims to expand and enhance the UpPair platform by digitizing manual workflows, integrating new business processes, and improving core functionalities. It includes the implementation of new digitization cases, platform automation, and scalability enhancements.
Key Deliverables | R/A/G | Delivery Date | Remarks on progress
Procurement Supplier Award Report (SARS) Digitization | G | 26 Sep 2025 | Requirements gathering has been completed. Business Partner, with input from Procurement, has finalized the PSD. Product Owner is currently performing technical analysis. Implementation will start on 7/7, with planned delivery by 26/9.
Digitization of forms & flows of the annual Enterprise Risk Assessment | G | 5 Dec 2025 | 2 alignment sessions completed. BP and Business working on detailed requirement documentation.
Investment Proposal Digitization | G | 27 Feb 2026 | Initial alignment held. Awaiting internal process readiness to proceed.
New Core Functionalities | G | Progressive delivery throughout project duration | Core functionalities will be progressively implemented in parallel with other digitization cases, based on prioritization and available team capacity. Specific deliveries will be aligned with ongoing analysis and business needs.
Additional Use Cases (Phase B) | G | 12 Jan 2027 | Further digitization cases are foreseen under Phase B. Future implementation steps will be based on the outcomes of the current analysis and prioritization.
Activities Performed & Milestones Achieved | Major Action Items - Upcoming Activities – Comments
Prioritization agreed: SARS to start first, followed by Risk Assessment and Investment Proposal. Requirements gathering finalized for SARS with support from business stakeholders. SARS documentation currently under internal analysis by Product Owner. | Start of SARS implementation scheduled for 7 July 2025 Enterprise Risk Assessment and Investment Proposal cases planned to follow in Q4 2025. Kick-off meeting to be held in July to align on overall approach and responsibilities. Post-implementation: Qualitative Assessment and Cost-Benefit Analysis. Definition of Merit Order based on findings to guide prioritization of any subsequent digitization cases.
Risk | Risk Assessment | Mitigation Actions
Delay in requirements documentation and analysis due to limited stakeholder availability or slow response times | M | Set clear deadlines, send reminders, and prioritize alignment meetings with BPs and Business Owners to keep momentum. Escalate if required.
Resource Availability | M | Upskill internal teams, align early with implementation teams on resource planning, and monitor workload across parallel projects.
Development Costs | M | Regular cost monitoring, budget contingency planning, early negotiations, and prioritize high-value features while deferring “nice to haves” to later phases.
ΙΤ Architecture & Tech Advancements | L | Conduct periodic reviews of IT architecture, plan phased adoption of new technologies, and allocate budget reserves for adjustments.

## Slide 7
7
SAP ID | JIRA ID | PM/BP | Business Owner | Involved Divisions
R/00031 | ID-174 | Koutsogiannakopoulos/ Drougkas | ENMA | DDDE,IT
Overall | Schedule | Cost | Scope
Project Status | Work Completed (%) | Baseline Budget | Planned Start Date | Planned/Estimated Completion Date
Procurement | 10% | 380K | 18 June 2025* | 24 Mar 2026
Phases/Milestones/Deliverables | R/A/G | Estimated Delivery Date | Remarks on progress
Expecting new Investment Approval for the Project | A | 08/25 | To Do
Contract Sign Off | A | TBD | Investment Approval will determine the contract sign-off date
Project Name | Distributed Energy Resources Management System
Activities Performed & Milestones Achieved | Major Action Items - Upcoming Activities - Comments
Prospective vendors' Presentations Technical Evaluation Negotiation and vendor selection concluded | Expecting new Investment Approval for the Project *Planned Start Date moved due to first RFP unfruitful attempt
Risk | Risk Assessment | Control
Possible change of scope for the second vendor, that might affect cost and schedule. | L | Adjust project plan with cooperation with business, and resubmit Investment Proposal, if needed.
Not enough clients for proper testing and deployment | M | Work with the Commercial Division to create the proper opportunities Find alternative, company-owned assets for testing
Project Scope | A Virtual power plant (VPP) system aggregates the capacity of diverse Distributed Energy Resources (DERs) dispersed around the network and creates an individual operating portfolio from the composition of DERs characteristics. VPPs can schedule the DERs to provide energy and different types of reserve services in order to trade in wholesale electricity markets or provide network services. A VPP system is required when managing many medium and small Distributed Energy Resources (generation, storage, flexible demand).

## Slide 8
8
SAP ID | JIRA ID | PM/BP | Business Owner | Involved Divisions
L/00080 | ID-212 | Koutsogiannakopoulos/ Drougkas | IT/DDDE | IT/DDDE
Overall | Schedule | Cost | Scope
Project Status | Work Completed (%) | Baseline Budget | Planned Start Date | Planned/Estimated Completion Date
Implementation | 85% | 150K | 3 Jun 2024 | 5 May 2025 / 11 July 2025
Phases/Milestones/Deliverables | R/A/G | Estimated Delivery Date | Remarks on progress
Phase 3¦ IT Dlv sign-off | G |  | Delays from vendors – issues raised from business
Phase 4 ¦ Produce Roadmap | G |  | Done
Phase 3 ¦ Review and sign-off | G |  | To Do
Phase 4¦ Produce supporting text for RFP | G |  | To Do
Phase 4¦ Review Roadmap and RFP and sign-off | G |  | To Do
Project Name | Data & IT Enterprise Architecture Study
Activities Performed & Milestones Achieved | Major Action Items - Upcoming Activities - Comments
Phase 2 ¦ Data Stream ¦ Deliverable accepted Phase 3 ¦ Data Stream ¦ Deliverable accepted Phase 2 ¦ IT Stream ¦Review completed | Phase 4 Roadmap submission as a conclusion of the project. Project to be signed off by 13/6 Issues of the deliverables are raised and expecting vendor feedback for project closure.
Risk | Risk Assessment | Control
Increase Demand for IT resources in combination with other projects running | L | Detailed project planning and alignment with other projects. Perform preparatory activities in parallel, in order to avoid/limit infrastructure operations downtime in IT
Alignment with Shareholder Strategy. To Be State may be impacted | L | Recurring ¦ obtain and evaluate provided input in terms of impact on the to be state
Non-timely engagement of the business and the data owners according to the requirement of the project | M | Perform preparatory activities to avoid/limit resource availability
Project Scope | Data Lake will serve as a singular, centralized data repository from which the Company’s data consumers can seamlessly access information. Depict As-Is Architecture and identify areas and tech improvements, define the To-Be model and alternative technological options on the target IT architecture and design the implementation roadmap.

## Slide 9
9
SAP ID | JIRA ID | PM/BP | Business Owner | Involved Divisions
L/00080 | ID-273 | Koutsogiannakopoulos/- | DDDE | DDDE
Overall | Schedule | Cost | Scope
Project Status | Work Completed (%) | Baseline Budget | Planned Start Date | Planned/Estimated Completion Date
Planning | 15% | 21K | TBD | TBD
Phases/Milestones/Deliverables | R/A/G | Estimated Delivery Date | Remarks on progress
Vendor Assignment | G | 19/6/25 | Done
Kick-Off | G | TBD | To Do
Data Review and Preparation | G | 7/7/025 | To Do
Project Name | Churn Model Upgrade
Activities Performed & Milestones Achieved | Major Action Items - Upcoming Activities - Comments
Investment Approval Financial Evaluation concluded | Project Plan finalization Issue: Delay from vendor to contract sign-off and initiation of the project Issue: Delay on Procurement negotiations to proceed to contract sign-off Issue: Delay on SAP Purchase Requisition Approval to proceed to procurement review
Project Scope | Elpedison will focus on retraining and upgrading the customer churn analytics solution, which was launched in 2024 Q1, to improve churn algorithm’s success rate and decrease churn %
Risk | Risk Assessment | Control
Plan may be delayed | L | Detailed project planning and alignment with other projects. Perform preparatory activities in parallel, in order to avoid/limit infrastructure operations downtime in IT

## Slide 10
10
SAP ID | JIRA ID | PM/BP | Business Owner | Involved Divisions
- | PMO-188 | Koutsogiannakopoulos/- | DDDE/IT/Legal/R&SP | All Company
Overall | Schedule | Cost | Scope
Project Status | Work Completed (%) | Baseline Budget | Planned Start Date | Planned/Estimated Completion Date
Implementation | 65% | - | 26/5/25 | 21/7/25
Phases/Milestones/Deliverables | R/A/G | Estimated Delivery Date | Remarks on progress
Phase A ¦ Application Documetation gathering and assessment | G | Done | In Progress – Workshop with vendors for high risk systems
Phase B ¦ Policies and Processes gathering and assessment – Gap Analysis | G | 11/7/25 | In Progress – Workshop with vendors for clarifications and guidance
Project Name | AI Act
Activities Performed & Milestones Achieved | Major Action Items - Upcoming Activities - Comments
Kick-off with HelleniQ Energy and the vendors AI System Registry Finalization and Classification | Bias & Fairness Monitoring Plan AI Procurement & Contractual Compliance Assessment Create Vendor Assessment Questionnaire Align with Regulatory Obligations AI Transparency & User Disclosure Protocol Ai Training & Awareness Programme This project executed jointly with HelleniQ Energy
Project Scope | The project aims to evaluate the effectiveness of the AI compliance framework, focusing on the identification and classification of AI systems, risk assessment processes, and the implementation of control mechanisms. It will assess the governance structure, ensuring roles and responsibilities are clearly defined, while also reviewing communication, transparency, and compliance monitoring systems to ensure ongoing adherence to regulatory requirements.
14/3/25 2/4/25
Risk | Risk Assessment | Control
Multiple stakeholder entities can lead to delays | L | Clear communication management plan and responsibilities distribution in place to mitigate this risk